## Sheet1
KATSINA STATE GOVERNMENT
STATE BUREAU OF PUBLIC PROCURMENT
NIGERIAN OPEN CONTRACTING PORTAL
PROCUREMENT PLAN
| MDA BUDGET YEAR | MINISTRY OF HEALTH
2025
S/N |  | PROJECT TITLE | PROJECT RATIONALE | PACKAGE NUMBER | LOT NUMBER | BUDGET SOURCE | BUDGET CODE | BUDGET DESCRIPTION | BUDGET CATEGORY | BUDGET CURRENCY | BUDGET AMOUNT | PROJECT ESTIMATED CURRENCY | PROJECT ESTIMATED AMOUNT | PROCUREMENT CATEGORY | CONTRACT TYPE | PROCUREMENT METHOD | SELECTION METHOD | APPROVAL AUTHORITY | QUALIFICATION | REVIEW TYPE | PREP FOR SOLICITE START DATE | PREP FOR SOLICITE END DATE | ADVERT START DATE | BID OPENING EVENT DATE | EVALUATE OF BID START DATE | EVALUATE OF BID END DATE | OPEN OF TECH PROPOSAL DATE | TECH EVAL REPORT APPROV START DATE | OPENING FINANCIAL PROPOSAL | FINAL EVAL REPORT T & F END DATE | NEGOTIATIONS START DATE | NEGOTIATIONS END DATE | PROC. ENTITY EVAL REPORT APPOV. START DATE | PROC. ENTITY EVAL REPORT APPOV. END DATE | AWARD DATE | CONTRACT PERIOD START DATE | CONTRACT PERIOD END DATE | CONTRACT PERIOD DAYS | ARIVAL OF GOODS START DATE | ARIVAL OF GOODS END DATE | FINANCIAL ACCEPTANCE START DATE | ACTION PARTY NAMES | ACTION PARTY DISIGNATION | ACTION PARTY E-MAIL | ACTION PARTY PHONE

## MOH 2
KATSINA STATE GOVERNMENT
STATE BUREAU OF PUBLIC PROCURMENT
NIGERIAN OPEN CONTRACTING PORTAL
PROCUREMENT PLAN
| MDA BUDGET YEAR | MINISTRY OF HEALTH
2025
S/N |  | PROJECT TITLE | PROJECT RATIONALE | PACKAGE NUMBER | LOT NUMBER | BUDGET SOURCE | BUDGET CODE | BUDGET DESCRIPTION | BUDGET CATEGORY | BUDGET CURRENCY | BUDGET AMOUNT | PROJECT ESTIMATED CURRENCY | PROJECT ESTIMATED AMOUNT | PROCUREMENT CATEGORY | CONTRACT TYPE | PROCUREMENT METHOD | SELECTION METHOD | APPROVAL AUTHORITY | QUALIFICATION | REVIEW TYPE | PREP FOR SOLICITE START DATE | PREP FOR SOLICITE END DATE | ADVERT START DATE | BID OPENING EVENT DATE | EVALUATE OF BID START DATE | EVALUATE OF BID END DATE | OPEN OF TECH PROPOSAL DATE | TECH EVAL REPORT APPROV START DATE | OPENING FINANCIAL PROPOSAL | FINAL EVAL REPORT T & F END DATE | NEGOTIATIONS START DATE | NEGOTIATIONS END DATE | PROC. ENTITY EVAL REPORT APPOV. START DATE | PROC. ENTITY EVAL REPORT APPOV. END DATE | AWARD DATE | CONTRACT PERIOD START DATE | CONTRACT PERIOD END DATE | CONTRACT PERIOD DAYS | ARIVAL OF GOODS START DATE | ARIVAL OF GOODS END DATE | FINANCIAL ACCEPTANCE START DATE | ACTION PARTY NAMES | ACTION PARTY DISIGNATION | ACTION PARTY E-MAIL | ACTION PARTY PHONE
OCTOBER
1 |  | CONSTRUCTION OF FOOD ANALYSIS AND QUALITY | TO IMPROVE THE
|  | CONTOL LABORATORY AT SCHOOL OF HEALTH TECHNOLO | CAPACITY OF HEALTH | MOH/WPD/CON/SHT/ |  | 2025 BUDGET |  |  |  | NIGERIAN NAIRA |  | NIGERIAN NAIRA | 37821205.75 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2025-06-10 | 2025-06-10 | 2026-06-01 | 3 MONTHS
|  | GY, KANKIA | INSTITUTION FACILITIES | DRA/2022/134/I
2 |  | CONSTRUCTION OF 2NO PUBLIC HEALTH NURSING | TO IMPROVE THE | MOH/WPD/CON/SON/ |  | 2025 BUDGET |  |  |  | NIGERIAN NAIRA |  | NIGERIAN NAIRA | 63443967.3 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2025-09-10 | 2025-09-10 | 2026-09-01 | 3 MONTHS
|  | LABORATORIES AT SCHOOL OF NURSING, KATSINA AND | CAPACITY OF HEALTH | 2021/110/I
|  | SCHOOL OF MIDWIFERY, MALUMFASHI | INSTITUTION FACILITIES
3 |  | CONSTRUCTION OF 1NO BLOCK OF FEMALE HOSTEL AT | TO IMPROVE THE | MOH/WPD/CON/SHT/ |  | 2025 BUDGET |  |  |  | NIGERIAN NAIRA |  | NIGERIAN NAIRA | 94717888 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 13/10/2025 | 13/10/2025 | 13/1/2026 | 3 MONTHS
|  | SCHOOL OF HEALTH TECHNOLOGY DAURA | CAPACITY OF HEALTH | DRA/2022/134/I
INSTITUTION FACILITIES
4 |  | RENOVATION OF DEMONSTRATION LABORATORY, | TO IMPROVE THE | MOH/WPD/CON/SON/ |  | 2025 BUDGET |  |  |  | NIGERIAN NAIRA |  | NIGERIAN NAIRA | 56450000 |  | RENOVATION AND REHABILITA | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2025-06-10 | 2025-06-10 | 2025-06-01 | 3 MONTHS
|  | LIBRARY, STAFF OFFICES AND STUDENT CLASSES AT | CAPACITY OF HEALTH | 2021/110/I | [10 empty] | TION
|  | NANA BABAJO SCHOOL OF MIDWIFERY, MALUMFASHI | INSTITUTION FACILITIES
5 |  | EXPANSION OF LIBRARY BLOCK AT KASIMU KOFAR BAI | TO IMPROVE THE | MOH/WPD/CON/SON/ |  | 2025 BUDGET |  |  |  | NIGERIAN NAIRA |  | NIGERIAN NAIRA | 38946694.6 |  | EXPANSION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2025-06-10 | 2025-06-10 | 2025-06-01 | 3 MONTHS
|  | COLLEGE OF NURSING SCIENCE SATELLITE CAMPUS, | CAPACITY OF HEALTH | DRA/2021/110/I
|  | KATSINA | INSTITUTION FACILITIES
6 |  | CONSTRUCTION OF 4NO LABORATORIES AND 1NO | TO IMPROVE THE | MOH/WPD/CON/SHT/ |  | 2025 BUDGET |  |  |  | NIGERIAN NAIRA |  | NIGERIAN NAIRA | 174943648.85 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 13/10/2025 | 13/10/2025 | 13/1/2026 | 3 MONTHS
|  | ENTREPRENEURSHIP CENTRE AT SCHOOL OF HEALTH | CAPACITY OF HEALTH | DRA/2022/134/I
|  | TECHNOLOGY DAURA | INSTITUTION FACILITIES
NOVEMBER
1 |  | PROVISION OF CRITICAL HOSPITAL EQUIPMENT NEEDED | TO IMPROVE HEALTH CARE | KHSMB/S.130/IV |  | 2025 BUDGET |  |  |  | NIGERIAN NAIRA |  | NIGERIAN NAIRA | 99412500 |  | SUPPLY | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 14/11/2025 | 14/11/2025 | 28/12/2025 | 6 WEEKS
|  | BY NEWLY QUALIFIED SPECIALIST WITH THE KATSINA | SERVICES
STATE GOVERNMENT
2 |  | PROCUREMENT OF BASIC MEDICAL EQUIPMENT ACROSS | TO IMPROVE HEALTH CARE |  |  | 2025 BUDGET |  |  |  | NIGERIAN NAIRA |  | NIGERIAN NAIRA | 75073931 |  | SUPPLY | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 13/11/2025 | 13/11/2025 | 29/11/2025 | 2 WEEKS
|  | HEALTH FACILITIES IN THE STATE | SERVICES
3 |  | RENOVATION OF OPERATING THEATRES AT GENERAL | TO IMPROVE HEALTH CARE | KHSMB/S.741/1 |  | 2025 BUDGET |  |  |  | NIGERIAN NAIRA |  | NIGERIAN NAIRA | 105777648.44 |  | RENOVATION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2025-11-11 | 2025-11-11 | 2025-11-01 | 8 WEEKS
|  | AMADI RIMI SPECIALIST HOSPITAL, KATSINA AND | SERVICES
GENERAL HOSPITAL, KATSINA