## Sheet1
STATE BUREAU OF PUBLIC PROCURMENT
NIGERIAN OPEN CONTRACTING PORTAL
PROCUREMENT PLAN
| MDA BUDGET YEAR | MINISTRY OF BASIC & SECONDARY EDUCATION
2026
S/N |  | PROJECT TITLE | PROJECT RATIONALE | PACKAGE NUMBER | LOT NUMBER | BUDGET SOURCE | BUDGET CODE | BUDGET DESCRIPTION | BUDGET CATEGORY | BUDGET CURRENCY | BUDGET AMOUNT | PROJECT ESTIMATED CURRENCY | PROJECT ESTIMATED AMOUNT | PROCUREMENT CATEGORY | CONTRACT TYPE | PROCUREMENT METHOD | SELECTION METHOD | APPROVAL AUTHORITY | QUALIFICATION | REVIEW TYPE | PREP FOR SOLICITE START DATE | PREP FOR SOLICITE END DATE | ADVERT START DATE | BID OPENING EVENT DATE | EVALUATE OF BID START DATE | EVALUATE OF BID END DATE | OPEN OF TECH PROPOSAL DATE | TECH EVAL REPORT APPROV START DATE | OPENING FINANCIAL PROPOSAL | FINAL EVAL REPORT T & F END DATE | NEGOTIATIONS START DATE | NEGOTIATIONS END DATE | PROC. ENTITY EVAL REPORT APPOV. START DATE | PROC. ENTITY EVAL REPORT APPOV. END DATE | AWARD DATE | CONTRACT PERIOD START DATE | CONTRACT PERIOD END DATE | CONTRACT PERIOD DAYS | ARIVAL OF GOODS START DATE | ARIVAL OF GOODS END DATE | FINANCIAL ACCEPTANCE START DATE | ACTION PARTY NAMES | ACTION PARTY DISIGNATION | ACTION PARTY E-MAIL | ACTION PARTY PHONE
| 2026-04-01 | Engagement of consultacy services to m/s MAHUTA to supervise construction of 30 no senior sec. schools Across the state | TO IMPROVE LEARNING ENVIROMENT | KTS/MBASE/CBP/GEN/394/VOL.III/0335 |  | 2026 BUDGET | 551700074 | Consultancy services |  | NIGERIAN NAIRA | 15000000000 | NIGERIAN NAIRA | 332937227.03 |  | consultacy servises | SELECTIVE TENDERING METHOD |  | exective council | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-03-02 | 2026-03-02 | as applicable |  |  |  |  | MIN OF BASIC & SEC. EDU. | DIRETOR WORKS |  | 8036251945
| 2026-04-01 | Supply of 3,000 units of Ev-motor cycles for distrubution to teachers serving in hard to reach Areas | TO IMPROVE the efficiency of teachers | KTS/MBASE/CBP/GEN/394/VOL.III/0363 |  | 2026 BUDGET | 551700074 | Procurement of Motor cycles |  | NIGERIAN NAIRA | 15000000000 | NIGERIAN NAIRA | 4083665640 |  | supply | SELECTIVE TENDERING METHOD | lowest bidder | exective council | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-03-25 | 2026-03-25 | 2026-06-25 | 90 days |  |  |  | MIN OF BASIC & SEC. EDU. | DIRETOR WORKS |  | 8036251945
| 2026-04-01 | Procurement of Customized Statutory & non Statutory books | TO IMPROVE LEARNING | KTS/MBASE/CBP/GEN/394/VOL.III/0321 |  | 2026 BUDGET | 551700233 | Procurement of Customized Statutory & non Statutory books |  | NIGERIAN NAIRA |  | NIGERIAN NAIRA | 111774500 |  | SUPPLY | SELECTIVE TENDERING METHOD | LOWEST BIDDER | BPP BOARD | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [22 empty] | MIN OF BASIC & SEC. EDU. | DIRETOR WORKS |  | 8036251945 | DIRETOR WORKS | 8036251945
| 2026-04-01 | Construction of perimeter wall at Dalatu Aminu masari Primary school. | TO IMPROVE LEARNING | KTS/SUBEB/OFF/336/VOL.I/8 |  | 2026 BUDGET |  | Construction of perimeter wall at Dalatu Aminu masari Primary school. |  | NIGERIAN NAIRA |  | NIGERIAN NAIRA | 52430261.96 |  | Construction | SELECTIVE TENDERING METHOD | LOWEST BIDDER | BPP BOARD | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 27/4/2026 | 27/4/2026 | 27/7/2026 | 120 |  |  |  | SUBEB | DIRECTOR PHYSICAL PLANING |  | 8130697119
| 2026-05-01 | Upgrading of perimeter wall fence,provion & instullation of solar light, and construction of two number 8000ltrs on 6m high tower weter scheme at GSS MALUMFASHI. | TO IMPROVE LEARNING | KTS/STEB/BLD/766/VOL1.I/ |  | 2026 BUDGET |  | Upgrading of perimeter wall fence,provion & instullation of solar light, and construction of two number 8000ltrs on 6m high tower weter scheme at GSS MALUMFASHI. |  | NIGERIAN NAIRA |  | NIGERIAN NAIRA | 158646868.17 |  | UPGRADING | SELECTIVE TENDERING METHOD | LOWEST BIDDER | BPP BOARD | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 18/5/2026 | 18/5/2026 | 18/7/2026 | 60 DAYS |  |  |  | MOBSE | DIRETOR WORKS |  | 8036251945
| 2026-05-01 | Procurement of WHITE BOARD MAKER, PHONICS BOOKS 1-3& LETTER GUIDE BOOK 1-2 | TO IMPROVE LEARNING | KTS/SUBEB/OFF/240/VOL.1/13 |  | 2026 BUDGET | 22020310 | Procurement of WHITE BOARD MAKER, PHONICS BOOKS 1-3& LETTER GUIDE BOOK 1-2 |  | NIGERIAN NAIRA |  | NIGERIAN NAIRA | 118850000 |  | SUPPLY | SELECTIVE TENDERING METHOD | SELECTIVE TENDERING METHOD | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | lowest bidder |  |  | 2026-04-20 | 2026-04-28 | 2026-04-28 | 2026-04-28 | [11 empty] | 14 Days |  |  |  | SUBEB | DIRECTOR PHYSICAL PLANING |  | 8130697119
| 2026-05-01 | Supply of Essential & Learning meterials for the 2026/2027 acadermic session | TO IMPROVE LEARNING | KTS/SUBEB/OFF/240/VOL.1/12 |  | 2026 BUDGET | 22020310 | Supply of Essential & Learning meterials for the 2026/2027 acadermic session |  | NIGERIAN NAIRA |  | NIGERIAN NAIRA | 118850000 |  | SUPPLY | SELECTIVE TENDERING METHOD | SELECTIVE TENDERING METHOD | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | lowest bidder | [14 empty] | 18/5/2026 | 18/5/2026 | 2026-01-06 | 14 days |  |  |  | SUBEB | DIRECTOR PHYSICAL PLANING |  | 8130697119
| 2026-05-26 | Renovation of 1no Burnt I-Shaped Dormitory & 2no. Additional 6-cubicles Toilets at GSSS Bindawa. | TO IMPROVE LEARNING | KTS/STEB/BLD/766/VOL.1/ |  | 2026 BUDGET | 551700207 | Renovation of 1no Burnt I-Shaped Dormitory & 2no. Additional 6-cubicles Toilets at GSSS Bindawa. |  | NIGERIAN NAIRA |  | NIGERIAN NAIRA | 37945308.61 |  | Renovation | SELECTIVE TENDERING METHOD | SELECTIVE TENDERING METHOD | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | lowest bidder |  |  | 2026-03-06 | [11 empty] | 2026-03-06 | 2026-03-06 | 2026-03-08 | 60 Days |  |  |  | MIN OF SCIENCE & TECH. EDU. BOARD | DIRETOR WORKS |  | 8130114588
[38 empty] | 84 Days |  |  |  | MIN OF BASIC & SEC. EDU. | DIRETOR WORKS |  | 8036251945