## Sheet1
NIGERIAN OPEN CONTRACTING PORTAL
PROCUREMENT PLAN
STATE PRIMARY HEALTH CARE AGENCY
| MDA BUDGET YEAR | 2026
S/N |  | PROJECT TITLE | PROJECT RATIONALE | PACKAGE NUMBER | LOT NUMBER | BUDGET SOURCE | BUDGET CODE | BUDGET DESCRIPTION | BUDGET CATEGORY | BUDGET CURRENCY | BUDGET AMOUNT | PROJECT ESTIMATED CURRENCY | PROJECT ESTIMATED AMOUNT | PROCUREMENT CATEGORY | CONTRACT TYPE | PROCUREMENT METHOD | SELECTION METHOD | APPROVAL AUTHORITY | QUALIFICATION | REVIEW TYPE | PREP FOR SOLICITE START DATE | PREP FOR SOLICITE END DATE | ADVERT START DATE | BID OPENING EVENT DATE | EVALUATE OF BID START DATE | EVALUATE OF BID END DATE | OPEN OF TECH PROPOSAL DATE | TECH EVAL REPORT APPROV START DATE | OPENING FINANCIAL PROPOSAL | FINAL EVAL REPORT T & F END DATE | NEGOTIATIONS START DATE | NEGOTIATIONS END DATE | PROC. ENTITY EVAL REPORT APPOV. START DATE | PROC. ENTITY EVAL REPORT APPOV. END DATE | AWARD DATE | CONTRACT PERIOD START DATE | CONTRACT PERIOD END DATE | CONTRACT PERIOD DAYS | ARIVAL OF GOODS START DATE | ARIVAL OF GOODS END DATE | FINANCIAL ACCEPTANCE START DATE | ACTION PARTY NAMES | ACTION PARTY DISIGNATION | ACTION PARTY E-MAIL | ACTION PARTY PHONE
APRIL
1 |  | CONSTRUCTION OF STAFF QUARTERS TO 26NO PRIMARY HEALTH CARE CENTRES (PHCS) REVITALISED UNDER PHCS MOU ACROSS 34 LGAS IN KATSINA STATE (TABANNI, MUSAWA). | TO IMPROVE WORKING CONDITION OF STAFF | SPHCA/ADM/03/VOL.1/123 |  | 2026 BUDGET | 4521001540 | CAPITAL PROJECT under UPGRADE OF PHCs TO FUNCTIONAL CHCs |  | NIGERIAN NAIRA | 5000000000 | NIGERIAN NAIRA | 28402252.75 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-04-22 | 2026-04-22 | 2026-08-22 | 120 Days |  |  |  | PRIMARY HEALTH CARE AGENCY | DIRECTOR WORKS |  | 8037211490
2 |  | CONSTRUCTION OF STAFF QUARTERS TO 26NO PRIMARY HEALTH CARE CENTRES (PHCS) REVITALISED UNDER PHCS MOU ACROSS 34 LGAS IN KATSINA STATE (DUTSIN-MA, DUTSIN-MA). | TO IMPROVE WORKING CONDITION OF STAFF | SPHCA/ADM/03/VOL.1/123 |  | 2026 BUDGET | 4521001540 | CAPITAL PROJECT under UPGRADE OF PHCs TO FUNCTIONAL CHCs |  | NIGERIAN NAIRA | 5000000000 | NIGERIAN NAIRA | 28402252.75 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-04-22 | 2026-04-22 | 2026-08-22 | 120 Days |  |  |  | PRIMARY HEALTH CARE AGENCY | DIRECTOR WORKS |  | 8037211490
3 |  | CONSTRUCTION OF STAFF QUARTERS TO 26NO PRIMARY HEALTH CARE CENTRES (PHCS) REVITALISED UNDER PHCS MOU ACROSS 34 LGAS IN KATSINA STATE (BARAJE, DAURA). | TO IMPROVE WORKING CONDITION OF STAFF | SPHCA/ADM/03/VOL.1/123 |  | 2026 BUDGET | 4521001540 | CAPITAL PROJECT under UPGRADE OF PHCs TO FUNCTIONAL CHCs |  | NIGERIAN NAIRA | 5000000000 | NIGERIAN NAIRA | 28402252.75 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-04-22 | 2026-04-22 | 2026-08-22 | 120 Days |  |  |  | PRIMARY HEALTH CARE AGENCY | DIRECTOR WORKS |  | 8037211490
4 |  | CONSTRUCTION OF STAFF QUARTERS TO 26NO PRIMARY HEALTH CARE CENTRES (PHCS) REVITALISED UNDER PHCS MOU ACROSS 34 LGAS IN KATSINA STATE (PHC SABON GARI, RIMI). | TO IMPROVE WORKING CONDITION OF STAFF | SPHCA/ADM/03/VOL.1/123 |  | 2026 BUDGET | 4521001540 | CAPITAL PROJECT under UPGRADE OF PHCs TO FUNCTIONAL CHCs |  | NIGERIAN NAIRA | 5000000000 | NIGERIAN NAIRA | 28402252.75 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-04-22 | 2026-04-22 | 2026-08-22 | 120 Days |  |  |  | PRIMARY HEALTH CARE AGENCY | DIRECTOR WORKS |  | 8037211490
5 |  | CONSTRUCTION OF STAFF QUARTERS TO 26NO PRIMARY HEALTH CARE CENTRES (PHCS) REVITALISED UNDER PHCS MOU ACROSS 34 LGAS IN KATSINA STATE (DANMUSA, DANMUSA LGA). | TO IMPROVE WORKING CONDITION OF STAFF | SPHCA/ADM/03/VOL.1/123 |  | 2026 BUDGET | 4521001540 | CAPITAL PROJECT under UPGRADE OF PHCs TO FUNCTIONAL CHCs |  | NIGERIAN NAIRA | 5000000000 | NIGERIAN NAIRA | 28402252.75 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-04-22 | 2026-04-22 | 2026-08-22 | 120 Days |  |  |  | PRIMARY HEALTH CARE AGENCY | DIRECTOR WORKS |  | 8037211490
6 |  | CONSTRUCTION OF STAFF QUARTERS TO 26NO PRIMARY HEALTH CARE CENTRES (PHCS) REVITALISED UNDER PHCS MOU ACROSS 34 LGAS IN KATSINA STATE (PHC YARMALULU, BAURE LGA). | TO IMPROVE WORKING CONDITION OF STAFF | SPHCA/ADM/03/VOL.1/123 |  | 2026 BUDGET | 4521001540 | CAPITAL PROJECT under UPGRADE OF PHCs TO FUNCTIONAL CHCs |  | NIGERIAN NAIRA | 5000000000 | NIGERIAN NAIRA | 28402252.75 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-04-22 | 2026-04-22 | 2026-08-22 | 120 Days |  |  |  | PRIMARY HEALTH CARE AGENCY | DIRECTOR WORKS |  | 8037211490
7 |  | CONSTRUCTION OF STAFF QUARTERS TO 26NO PRIMARY HEALTH CARE CENTRES (PHCS) REVITALISED UNDER PHCS MOU ACROSS 34 LGAS IN KATSINA STATE (FAGO, SANDAMU). | TO IMPROVE WORKING CONDITION OF STAFF | SPHCA/ADM/03/VOL.1/123 |  | 2026 BUDGET | 4521001540 | CAPITAL PROJECT under UPGRADE OF PHCs TO FUNCTIONAL CHCs |  | NIGERIAN NAIRA | 5000000000 | NIGERIAN NAIRA | 28402252.75 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-04-22 | 2026-04-22 | 2026-08-22 | 120 Days |  |  |  | PRIMARY HEALTH CARE AGENCY | DIRECTOR WORKS |  | 8037211490
8 |  | CONSTRUCTION OF STAFF QUARTERS TO 26NO PRIMARY HEALTH CARE CENTRES (PHCS) REVITALISED UNDER PHCS MOU ACROSS 34 LGAS IN KATSINA STATE (PHC MAKURDA, RIMI). | TO IMPROVE WORKING CONDITION OF STAFF | SPHCA/ADM/03/VOL.1/123 |  | 2026 BUDGET | 4521001540 | CAPITAL PROJECT under UPGRADE OF PHCs TO FUNCTIONAL CHCs |  | NIGERIAN NAIRA | 5000000000 | NIGERIAN NAIRA | 28402252.75 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-04-22 | 2026-04-22 | 2026-08-22 | 120 Days |  |  |  | PRIMARY HEALTH CARE AGENCY | DIRECTOR WORKS |  | 8037211490
9 |  | CONSTRUCTION OF STAFF QUARTERS TO 26NO PRIMARY HEALTH CARE CENTRES (PHCS) REVITALISED UNDER PHCS MOU ACROSS 34 LGAS IN KATSINA STATE (KONGOLOM, MAI ADUA). | TO IMPROVE WORKING CONDITION OF STAFF | SPHCA/ADM/03/VOL.1/123 |  | 2026 BUDGET | 4521001540 | CAPITAL PROJECT under UPGRADE OF PHCs TO FUNCTIONAL CHCs |  | NIGERIAN NAIRA | 5000000000 | NIGERIAN NAIRA | 28402252.75 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-04-22 | 2026-04-22 | 2026-08-22 | 120 Days |  |  |  | PRIMARY HEALTH CARE AGENCY | DIRECTOR WORKS |  | 8037211490
10 |  | CONSTRUCTION OF STAFF QUARTERS TO 26NO PRIMARY HEALTH CARE CENTRES (PHCS) REVITALISED UNDER PHCS MOU ACROSS 34 LGAS IN KATSINA STATE (FAKUWA, KANKIA). | TO IMPROVE WORKING CONDITION OF STAFF | SPHCA/ADM/03/VOL.1/123 |  | 2026 BUDGET | 4521001540 | CAPITAL PROJECT under UPGRADE OF PHCs TO FUNCTIONAL CHCs |  | NIGERIAN NAIRA | 5000000000 | NIGERIAN NAIRA | 28402252.75 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-04-22 | 2026-04-22 | 2026-08-22 | 120 Days |  |  |  | PRIMARY HEALTH CARE AGENCY | DIRECTOR WORKS |  | 8037211490
11 |  | CONSTRUCTION OF STAFF QUARTERS TO 26NO PRIMARY HEALTH CARE CENTRES (PHCS) REVITALISED UNDER PHCS MOU ACROSS 34 LGAS IN KATSINA STATE (TUDUN WADA, FUNTUA). | TO IMPROVE WORKING CONDITION OF STAFF | SPHCA/ADM/03/VOL.1/123 |  | 2026 BUDGET | 4521001540 | CAPITAL PROJECT under UPGRADE OF PHCs TO FUNCTIONAL CHCs |  | NIGERIAN NAIRA | 5000000000 | NIGERIAN NAIRA | 28402252.75 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-04-22 | 2026-04-22 | 2026-08-22 | 120 Days |  |  |  | PRIMARY HEALTH CARE AGENCY | DIRECTOR WORKS |  | 8037211490
12 |  | CONSTRUCTION OF STAFF QUARTERS TO 26NO PRIMARY HEALTH CARE CENTRES (PHCS) REVITALISED UNDER PHCS MOU ACROSS 34 LGAS IN KATSINA STATE ( PHC DUWAN, MANI LGA). | TO IMPROVE WORKING CONDITION OF STAFF | SPHCA/ADM/03/VOL.1/123 |  | 2026 BUDGET | 4521001540 | CAPITAL PROJECT under UPGRADE OF PHCs TO FUNCTIONAL CHCs |  | NIGERIAN NAIRA | 5000000000 | NIGERIAN NAIRA | 28402252.75 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-04-22 | 2026-04-22 | 2026-08-22 | 120 Days |  |  |  | PRIMARY HEALTH CARE AGENCY | DIRECTOR WORKS |  | 8037211490
13 |  | CONSTRUCTION OF STAFF QUARTERS TO 26NO PRIMARY HEALTH CARE CENTRES (PHCS) REVITALISED UNDER PHCS MOU ACROSS 34 LGAS IN KATSINA STATE ( PHC MAZOJI, MATAZU LGA). | TO IMPROVE WORKING CONDITION OF STAFF | SPHCA/ADM/03/VOL.1/123 |  | 2026 BUDGET | 4521001540 | CAPITAL PROJECT under UPGRADE OF PHCs TO FUNCTIONAL CHCs |  | NIGERIAN NAIRA | 5000000000 | NIGERIAN NAIRA | 28402252.75 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-04-22 | 2026-04-22 | 2026-08-22 | 120 Days |  |  |  | PRIMARY HEALTH CARE AGENCY | DIRECTOR WORKS |  | 8037211490
14 |  | CONSTRUCTION OF STAFF QUARTERS TO 26NO PRIMARY HEALTH CARE CENTRES (PHCS) REVITALISED UNDER PHCS MOU ACROSS 34 LGAS IN KATSINA STATE ( PHC YANKARA, FASKARI LGA). | TO IMPROVE WORKING CONDITION OF STAFF | SPHCA/ADM/03/VOL.1/123 |  | 2026 BUDGET | 4521001540 | CAPITAL PROJECT under UPGRADE OF PHCs TO FUNCTIONAL CHCs |  | NIGERIAN NAIRA | 5000000000 | NIGERIAN NAIRA | 28402252.75 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-04-22 | 2026-04-22 | 2026-08-22 | 120 Days |  |  |  | PRIMARY HEALTH CARE AGENCY | DIRECTOR WORKS |  | 8037211490
15 |  | CONSTRUCTION OF STAFF QUARTERS TO 26NO PRIMARY HEALTH CARE CENTRES (PHCS) REVITALISED UNDER PHCS MOU ACROSS 34 LGAS IN KATSINA STATE ( PHC YANKWANI, BAKORI LGA). | TO IMPROVE WORKING CONDITION OF STAFF | SPHCA/ADM/03/VOL.1/123 |  | 2026 BUDGET | 4521001540 | CAPITAL PROJECT under UPGRADE OF PHCs TO FUNCTIONAL CHCs |  | NIGERIAN NAIRA | 5000000000 | NIGERIAN NAIRA | 28402252.75 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-04-22 | 2026-04-22 | 2026-08-22 | 120 Days |  |  |  | PRIMARY HEALTH CARE AGENCY | DIRECTOR WORKS |  | 8037211490
16 |  | CONSTRUCTION OF STAFF QUARTERS TO 26NO PRIMARY HEALTH CARE CENTRES (PHCS) REVITALISED UNDER PHCS MOU ACROSS 34 LGAS IN KATSINA STATE ( PHC BUJAWA,MANI LGA). | TO IMPROVE WORKING CONDITION OF STAFF | SPHCA/ADM/03/VOL.1/123 |  | 2026 BUDGET | 4521001540 | CAPITAL PROJECT under UPGRADE OF PHCs TO FUNCTIONAL CHCs |  | NIGERIAN NAIRA | 5000000000 | NIGERIAN NAIRA | 28402252.75 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-04-22 | 2026-04-22 | 2026-08-22 | 120 Days |  |  |  | PRIMARY HEALTH CARE AGENCY | DIRECTOR WORKS |  | 8037211490
17 |  | CONSTRUCTION OF STAFF QUARTERS TO 26NO PRIMARY HEALTH CARE CENTRES (PHCS) REVITALISED UNDER PHCS MOU ACROSS 34 LGAS IN KATSINA STATE ( PHC GIDAN MUTUM DAYA,KUSADA LGA). | TO IMPROVE WORKING CONDITION OF STAFF | SPHCA/ADM/03/VOL.1/123 |  | 2026 BUDGET | 4521001540 | CAPITAL PROJECT under UPGRADE OF PHCs TO FUNCTIONAL CHCs |  | NIGERIAN NAIRA | 5000000000 | NIGERIAN NAIRA | 28402252.75 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-04-22 | 2026-04-22 | 2026-08-22 | 120 Days |  |  |  | PRIMARY HEALTH CARE AGENCY | DIRECTOR WORKS |  | 8037211490
18 |  | CONSTRUCTION OF STAFF QUARTERS TO 26NO PRIMARY HEALTH CARE CENTRES (PHCS) REVITALISED UNDER PHCS MOU ACROSS 34 LGAS IN KATSINA STATE ( PHC MUDURU, MANI LGA). | TO IMPROVE WORKING CONDITION OF STAFF | SPHCA/ADM/03/VOL.1/123 |  | 2026 BUDGET | 4521001540 | CAPITAL PROJECT under UPGRADE OF PHCs TO FUNCTIONAL CHCs |  | NIGERIAN NAIRA | 5000000000 | NIGERIAN NAIRA | 28402252.75 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-04-22 | 2026-04-22 | 2026-08-22 | 120 Days |  |  |  | PRIMARY HEALTH CARE AGENCY | DIRECTOR WORKS |  | 8037211490
19 |  | CONSTRUCTION OF STAFF QUARTERS TO 26NO PRIMARY HEALTH CARE CENTRES (PHCS) REVITALISED UNDER PHCS MOU ACROSS 34 LGAS IN KATSINA STATE ( PHC MALUMFASHI,MALUMFASHI LGA). | TO IMPROVE WORKING CONDITION OF STAFF | SPHCA/ADM/03/VOL.1/123 |  | 2026 BUDGET | 4521001540 | CAPITAL PROJECT under UPGRADE OF PHCs TO FUNCTIONAL CHCs |  | NIGERIAN NAIRA | 5000000000 | NIGERIAN NAIRA | 28402252.75 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-04-22 | 2026-04-22 | 2026-08-22 | 120 Days |  |  |  | PRIMARY HEALTH CARE AGENCY | DIRECTOR WORKS |  | 8037211490
20 |  | CONSTRUCTION OF STAFF QUARTERS TO 26NO PRIMARY HEALTH CARE CENTRES (PHCS) REVITALISED UNDER PHCS MOU ACROSS 34 LGAS IN KATSINA STATE ( PHC DANKABA,KAITA LGA). | TO IMPROVE WORKING CONDITION OF STAFF | SPHCA/ADM/03/VOL.1/123 |  | 2026 BUDGET | 4521001540 | CAPITAL PROJECT under UPGRADE OF PHCs TO FUNCTIONAL CHCs |  | NIGERIAN NAIRA | 5000000000 | NIGERIAN NAIRA | 28402252.75 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-04-22 | 2026-04-22 | 2026-08-22 | 120 Days |  |  |  | PRIMARY HEALTH CARE AGENCY | DIRECTOR WORKS |  | 8037211490
21 |  | CONSTRUCTION OF STAFF QUARTERS TO 26NO PRIMARY HEALTH CARE CENTRES (PHCS) REVITALISED UNDER PHCS MOU ACROSS 34 LGAS IN KATSINA STATE ( PHC DUTSIN SAFE LOWCOST, KATSINA LGA). | TO IMPROVE WORKING CONDITION OF STAFF | SPHCA/ADM/03/VOL.1/123 |  | 2026 BUDGET | 4521001540 | CAPITAL PROJECT under UPGRADE OF PHCs TO FUNCTIONAL CHCs |  | NIGERIAN NAIRA | 5000000000 | NIGERIAN NAIRA | 28402252.75 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-04-22 | 2026-04-22 | 2026-08-22 | 120 Days |  |  |  | PRIMARY HEALTH CARE AGENCY | DIRECTOR WORKS |  | 8037211490
22 |  | CONSTRUCTION OF STAFF QUARTERS TO 26NO PRIMARY HEALTH CARE CENTRES (PHCS) REVITALISED UNDER PHCS MOU ACROSS 34 LGAS IN KATSINA STATE ( PHC BARKIYA, KURFI LGA). | TO IMPROVE WORKING CONDITION OF STAFF | SPHCA/ADM/03/VOL.1/123 |  | 2026 BUDGET | 4521001540 | CAPITAL PROJECT under UPGRADE OF PHCs TO FUNCTIONAL CHCs |  | NIGERIAN NAIRA | 5000000000 | NIGERIAN NAIRA | 28402252.75 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-04-22 | 2026-04-22 | 2026-08-22 | 120 Days |  |  |  | PRIMARY HEALTH CARE AGENCY | DIRECTOR WORKS |  | 8037211490
23 |  | CONSTRUCTION OF STAFF QUARTERS TO 26NO PRIMARY HEALTH CARE CENTRES (PHCS) REVITALISED UNDER PHCS MOU ACROSS 34 LGAS IN KATSINA STATE ( PHC NAHUCE, DANJA LGA). | TO IMPROVE WORKING CONDITION OF STAFF | SPHCA/ADM/03/VOL.1/123 |  | 2026 BUDGET | 4521001540 | CAPITAL PROJECT under UPGRADE OF PHCs TO FUNCTIONAL CHCs |  | NIGERIAN NAIRA | 5000000000 | NIGERIAN NAIRA | 28402252.75 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-04-22 | 2026-04-22 | 2026-08-22 | 120 Days |  |  |  | PRIMARY HEALTH CARE AGENCY | DIRECTOR WORKS |  | 8037211490
24 |  | CONSTRUCTION OF STAFF QUARTERS TO 26NO PRIMARY HEALTH CARE CENTRES (PHCS) REVITALISED UNDER PHCS MOU ACROSS 34 LGAS IN KATSINA STATE ( PHC KOFAR GUGA, KATSINA LGA). | TO IMPROVE WORKING CONDITION OF STAFF | SPHCA/ADM/03/VOL.1/123 |  | 2026 BUDGET | 4521001540 | CAPITAL PROJECT under UPGRADE OF PHCs TO FUNCTIONAL CHCs |  | NIGERIAN NAIRA | 5000000000 | NIGERIAN NAIRA | 28402252.75 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-04-22 | 2026-04-22 | 2026-08-22 | 120 Days |  |  |  | PRIMARY HEALTH CARE AGENCY | DIRECTOR WORKS |  | 8037211490
25 |  | CONSTRUCTION OF STAFF QUARTERS TO 26NO PRIMARY HEALTH CARE CENTRES (PHCS) REVITALISED UNDER PHCS MOU ACROSS 34 LGAS IN KATSINA STATE ( PHC RIMI, RIMI LGA). | TO IMPROVE WORKING CONDITION OF STAFF | SPHCA/ADM/03/VOL.1/123 |  | 2026 BUDGET | 4521001540 | CAPITAL PROJECT under UPGRADE OF PHCs TO FUNCTIONAL CHCs |  | NIGERIAN NAIRA | 5000000000 | NIGERIAN NAIRA | 28402252.75 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-04-22 | 2026-04-22 | 2026-08-22 | 120 Days |  |  |  | PRIMARY HEALTH CARE AGENCY | DIRECTOR WORKS |  | 8037211490
26 |  | CONSTRUCTION OF STAFF QUARTERS TO 26NO PRIMARY HEALTH CARE CENTRES (PHCS) REVITALISED UNDER PHCS MOU ACROSS 34 LGAS IN KATSINA STATE ( PHC KOFAR GUGA, KATSINA LGA). | TO IMPROVE WORKING CONDITION OF STAFF | SPHCA/ADM/03/VOL.1/123 |  | 2026 BUDGET | 4521001540 | CAPITAL PROJECT under UPGRADE OF PHCs TO FUNCTIONAL CHCs |  | NIGERIAN NAIRA | 5000000000 | NIGERIAN NAIRA | 28402252.75 |  | CONSTRUCTION | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-04-22 | 2026-04-22 | 2026-08-22 | 120 Days |  |  |  | PRIMARY HEALTH CARE AGENCY | DIRECTOR WORKS |  | 8037211490
27 | 2026-06-01 | Procurement of Basic Instruments & consumerbles for the Take-off of the newly upgaded General Hospital inZango LGA. | TO IMPROVE WORKING CONDITION OF STAFF | KHSMB/S.956/VOL.1 |  | 2026 BUDGET |  | SUPPLY |  | NIGERIAN NAIRA |  | NIGERIAN NAIRA | 60672078 | SUPPLY | SUPPLY | SELECTIVE TENDERING | LOWEST, RESP & EVAL BIDDER | BPP | BPP REG. CAC, ITF, PENCOM,TAX CLEARANCE | [15 empty] | 2026-06-11 | 2026-06-11 | 24/7/2026 | 42 Days |  |  |  | HEALTH SERVICE MANEGEMENT BOARD | DIRECTOR WORKS